## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
*Note: Any boxes that are greyed out are user stories and acceptance plans that are not finished and should not be tested.*
Team Name | 2191-swen-261-10-c C
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | SL; 10/1/2019
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | SL; 10/1/2019
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | SB; 10/8/2019; Initially thought finished on 10/1/2019, further testing revealed that spaces and numeric cases were not being accepted properly, tested again on 10/8/2019 to fix it
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | SB; 10/6/2019
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | SL; 10/1/2019
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | SB; 10/6/2019
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | SB; 10/6/2019
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | SB; 10/8/2019
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | SB; 10/8/2019
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | SB; 10/8/2019; Initially failed on testing on 10/8/2019, fixed and tested again for pass later on 10/8/2019
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | SL; 10/8/2019
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | EC; 10/8/2019
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | EC; 10/8/2019
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | EC; 10/8/2019
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | EC; 10/8/2019
Epic: Game Setup -- As a Player, I want to be able to start the game so that I can play a game of checkers.
As a Player I want to sign out of the server so that I can finish playing without forcefully exiting the application. | Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button)
Given that I have signed out then the name I had when I signed in is no longer reserved.
Given that I have signed out then in order to play another game I will have to sign-in.
Given that I have signed out when I try to sign in again then I should see the Home page.
As a Player I want to be able to resign from any game at any time so I can leave the game to do something else. | Given that I have signed in and I am playing a game when I want to leave the game then I must see a means to resign. (such as a link or button)
Given that I have resigned from the game then the game should end and the other player should not be able to play that game further.
Given that I resigned from the game then I should still be signed into the website.
Given that I want to resign from the game then I can resign from the game at any time.
Epic: Player Movement -- As a Player I want to move my piece so that I can play against my opponent.
As a Player I want to be able to make simple moves only so that I can follow the rules when making my turn. | Given that some legal move can be made when I make the move then I expect the board to change with respect to the move I make.
Given that the rules do not allow a move to be made when I move my piece to an illegal square then I expect the piece to not move and my turn to still be incomplete.
As a Player, I want to take my opponent's piece so that I can win the game. | Given that there is an opponent piece to the diagonal of my piece when my piece skips over the opponent then I expect my piece to remain in the new position.
Given that there is an opponent piece to the diagonal of my piece when I skip my piece over the opponent's piece then I except the opponent's piece to disappear.
Given that there is a chain of opponents when I skip over multiple pieces then I except the game to follow the same rules as capturing a single piece (see above acceptance criteria).
As a Player I want to make jump moves so that I can capture the opponent's pieces. | Given that I can make a jump move when I try to make a move then I expect a jump move to be made.
Given that I try to make a jump move over my own piece when I try to make that move then I expect the move to not be allowed.
Given that I can make a jump move when I try to make a non jump-move then it is not allowed.
Epic: King Checker Piece -- As a Player I want to use king checker pieces so that I have an advantage in the game.
As a Player I want to transform my checker piece into a king at the king-row so that I have a king piece in the checker game. | Given that my checker piece has not been captured when the checker piece reaches the king-row then the checker piece should become a king.
Given that my checker piece is a king then I should know it is a king due to its unique design.
Given that my checker piece is a king when I move the king piece to the king-row again then my piece should not change.
Given that my piece is a king when my opponent jumps the piece then I expect the king piece to be captured like a normal piece.
As a Player I want to be able to move the king piece diagonally forward and backward so that the piece and I have an advantage in the game. | Given that my checker piece is a king when have the king piece jump then I can jump forward and backward.
Given that my checker piece is a king when there are multiple jumps possible then I can choose which jump to use.
Given that my checker piece is a king when the piece is jumping over multiple pieces then the king can jump forward and backward to capture an opponent's piece.
As a Player I want the board to be updated when the opponent makes a move so that I can know the current state of the board. | Given it's the opponent's turn when the opponent makes a move then I want my board to be updated.
As a Player I want the game to end when either one side has no pieces or there are no legal moves so that we can see the result of the game. | Given a player has no legal moves when their turn comes then I EXPECT the game to end with them losing as the result.
Given a player has no pieces left when a turn would begin then I EXPECT the game to end with the player without pieces losing as a result.
Given the game is over when I won then I expect to be congratulated on my victory.
Given the game is over when I lose then I expect to be told that I lost.
Given the game is over when I try to move any pieces then I expect the board to be unresponsive.
Given that the game is over and the opponent player resigns then I expect to be told the opponent resigned.
As a Player I want to backup a move so that I can undo a tentative move I made. | Given I have made a move when decide to reverse that move then I can press the backup button to reverse my move.
Epic: Tournament Enhancement -- As a player I want to enter a tournament so that I can play a longer, more competitive series of games with multiple payers.
As a Player I want to enter a tournament so that I can participate in a tournament in which I want to play. | Given there is an available tournament when I enter the tournament then I expect to become a participant in the tournament.
As a Tournament Participant I want to be entered into games with other tournament participants so that I can advance through the tournament ladder. | Given I have entered a tournament when I am matched against a player then I expect to be entered into a game against that player.
Given that I am a tournament participant when I win a tournament game then I expect to be matched against my next opponent.
Given I have won my current tournament game when my next opponent has not finished their game then I expect to wait for my next opponent's game to finish.
As a Tournament Participant I want to view tournament statistics so that I can compare my performance to that of other tournament participants. | Given I am a tournament participant when tournament statistics are available then I expect to be able to view the tournament statistics.
Epic: Game Spectating Enhancement -- As a Player I want to spectate other players' games so that I can view games in progress.
As a Player I want to view a list of games in progress so that I can choose which game to spectate. | Given that I want to spectate a game when I indicate that I would like to spectate a game then I expect to see a list of all games in progress.
Given that I am viewing a list of games in progress when I inspect a listed game in progress then I expect to see the names of the players who are playing in the game.
As a Spectator I want to stop spectating a game so that I can begin spectating or playing another game. | Given that I am spectating a game when the game ends then I want to be notified that the game has ended.
Given that I am spectating a game when I choose to stop spectating then the spectated game's board should be removed from my game view.
As a Player I want to see changes in the board of the game I am spectating so that I can watch the gameplay as it happens. | Given that I am spectating a game when a player makes a move then I want my view of the board to be updated immediately.
Given that I am spectating a game when I attempt to move a piece then nothing will happen.
As a Player I want to be choose a game to spectate so that I can begin viewing the game. | Given that I know which game I want to spectate when I select this game for spectating then I expect to be shown the game board in its current state.